## SEP Project Plan
Task | Category | When | Assigned to
Once Pinkerton Funding is confirmed Request Nominations from Partner Schools for 2026-2027 requesting the submit by June 26, 2026 - date coincides with NYC DOE last school day | Recruitment | end of June 2026
Schedule school site visits for Spring 2026 typically May 2026 works best for partner schools to speak with Sophomore class who are nominated ot apply | Recruitment | end of May 2026
Review Slate Applicaton and update SEP Notification Templates, Commitment Agreements send to Justina Vargas and Rosalinda Jose | Operations | July to August 2026
Send Invitations to SEP course facilitators, please refer to curriculum tab for facilitator contact info | Operations | September 2025 to October 2025
Send SEP nominees invitation to apply; application opens after SEP is complete, potential opening date is August 24, 2026 | Application | last week of August 2026
SEP application review with Dr Chakravarty, Yaihara and Raia Mohammed | Recruitment | Tuesday, September 9, 2025 to Tuesday September 16, 2025
Once final SEP selections are made enter in Slate and send admission notifications | Recruitment | Wednesday September 17, 2025
Once SEP students have confirmed their participation, enter requisitions in Workday. Job Code is 008019 and Job Title is Intern (Non-Seasonal); send list of students to HR inform them requisitions were entered | Onboarding | Friday September 19, 2025
Once HR confirms the Onboarding Forms (Medical Clearance etc) are updated send general email to 2025-2026 SEP students to complete the onboarding link sent from HR to begin their process. Be sure to cc the SEP school partners and parents so their aware of the onboarding criteria | Onboarding | mid September 2025 to end of October 2025
Set up weekly calls with HR Onboarding coordinator get status updates on students clearance status, send reminder email to students and cc parents about pending documentation | Onboarding | mid September 2025 to end of October 2025
Students should submit headshots with white background; photos will be sent to MSK security (Mamadou Diallo) to pre-print their MSK ID Badges | Onboarding | October 2025 to November 2025
Prepare 2025-2026 Orientation Packet; refer to Sciencetraining High School Programs SEP 2024-2025 folder for past orientation packet | Orientation | mid October 2025
Order weekly dinner, for students keep dinner order to approx $150; please use tax exempt form if submitting order online via EZ cater, Sandy has tax exempt form | Operations | Ongoing
Create Moodle class for 2025-2026 SEP contact Rosalinda Jose to assist in creating a page, once students are fully onboarded after orientation, invite students to the moodle page as students | Operations | Ongoing
Keep track of weekly attendance of students | Operations | Ongoing
Prior to first Cancer Biology lecture with Dr Chakravarty send student Biology Quiz, share results with Dr Chakravarty this will help her assess the baseline knowledge of students
Send reminder email to course facilitators a week in advance to confirm their course date/time and request if they have pre-course or post-course readings/assignments to send the students | Operations | Ongoing
After course please have facilitator send a pdf copy of their slides for your to post on the moodle course | Operations | Ongoing
All courses should be recorded, so set up a teams link and send to facilitator so when projecting their slides they are also logged on to the Teams meeting link so you can post the recording and slides together | Operations | Ongoing
Midterm Exam and Final Exam Preperation - coordinate with Dr Chakravarty by sending course topics/notes, post exam study guides in Moodle | Operations | Ongoing
Proctor Midterm and Final Exams virtually via Teams, the exams are found in Google Forms | Operations | Ongoing
Schedule 1:1 meeting with students: (1) the start of SEP, (2) after the midterm exam to assess performance and research interests, (3) start of lab placements and (4) checkin meeting mid-way to lab placements | Operations | Ongoing
Set up checkin 2 meetings with SEP Partner Schools: (1) Mid-February after midterm exam to assess student performance, (2) June after final exam and to share research placements of their students | Operations | Mid-February 2026 and end-June 2026
Collect alumni metrics for 2024-2025 SEP students, specifically list of college acceptances, financial aid award, anticipate college major, reference metrics spreadsheet in shared drive | Operations | April 2026 to June 2026
Contact Faculty for student lab placements | Operations | February 2026 to April 2026
Lab placements half of the cohort should be placed in Computational lab the other half in wet labs | Operations | February 2026 to April 2026
Contact Development - Mary Reed Holman to review finances and resubmitting Pinkerton Renewal Report; for 2026 this report will need to be submitted with Epi-Bio - Esther Drill, Kay See Tan and Richard Koppenaal join grant submission | Finances | January 2026 to February 2026
Coordinate Spring 2026 site visits with Pinkerton Foundation Program Officer - Jennifer Negron and NYC Science Research Mentoring Consortium - Arden Feil and Maria Strangas | Operations | early March 2026
Attend Quarterly NYC Science Research Mentoring Consortium Meetings at American Museum of Natural History, contact Arden Feil and Maria Strangas for 2026-2026 meeting schedule | Operations | Ongoing
Attend Quarterly NYC-STEM-Education-Network virtual meetings, contact Ashley R Johndon STEM director for meeting schedule ajohnson@expandedschools.org | Operations | ongoing
All lab placements should be confirmed by faculty | Operations | end of May 2026
Email faculty requesting they identify the lab member who will serve as students day to day mentor | Operations | by mid June 2026
Schedule 1:1 mentor meetings to go over student profile and SEP objectives, mentor expectations, meeting should highlight that OSET team to partner and provide any support needed during their mentorship experience | Operations | complete by mid to end of June 2026
Finalize summer SEP schedule, which includes SSP programming and NYC Science Research Mentoring Consortium summer events | Operations | May 2026 to June 2026
Send Mentor and Student feedback surveys to assess program and summer placement experiences | Operations | end of August 2026
Capture Alumni metrics in spreadsheet, connect with students on LinkedIn to capture academic progresss | Operations | Ongoing

## 2025-2026 SEP Curriculum
Date | Time | Location | Class Title | Class Category | Facilitator | Facilitator Email
2025-11-05 | 4:30PM - 6:00PM | ZRC-104 | Program Overview/ Student Expectations & Professionalism in the Workplace & Personality Assessment | Programatic | Yaihara Fortis-Santiago/Raia Mohammed/Kevin Fisher | fortissy@mskcc.org/mohammer@mskcc.org
2025-11-12 | 4:30PM - 6:00PM | Zoom | 2024-2025 SEP Alumni: Potential Panelist (Alexander Martinez, Rocio Garcia, Daniela Gonzalez Placencia, Nya Lataillade, Jaylen McDonald, Sarah Segura) | Professional Dev | Yaihara Fortis-Santiago/Raia Mohammed/Kevin Fisher | fortissy@mskcc.org/mohammer@mskcc.org
2025-11-19 | 4:30PM - 6:00PM | Zoom | Professional Development: Navigating the STEM Academic Journey ( talk about paths through science and medicine) Sangita Chakraborty (Bridge)/ Diego Rodriguez (MD PhD student) /Dylan Manuele(med student) | Professional Dev | Yaihara Fortis-Santiago | fortissy@mskcc.org/mohammer@mskcc.org
2025-11-26 |  | No Class - Day Before Thanksgiving Day Holiday | No Class - Thanksgiving Day Holiday | N/A
2025-12-03 | 4:30PM - 6:00PM | ZRC-466 | Professional Development: How to Read a Journal Article | Professional Dev | Dr Jerry Melchor, Jonathan Bermeo | melchorj@mskcc.org; bermeoj@mskcc.org
2025-12-10 | 4:30PM - 6:00PM | Macklowe Building, 323 E. 61st St NY, NY 10065, Conference Room 530 | Cancer Biology: Into & Fundamentals of Biology (I and II) (Pop Quiz) | Cancer Biology | Dr Debyani Chakravarty | chakravd@mskcc.org
2025-12-17 | 4:30PM - 6:00PM | ZRC-466 | Cancer Biology: The Nature of Cancer | Cancer Biology | Ana Codo | codoa1@mskcc.org
2025-12-24 |  | No Class - Winter Break | No Class - Winter Break | N/A
2025-12-31 |  | No Class - Winter Break | No Class - Winter Break | N/A
2026-01-07 | 4:30PM - 6:00PM | ZRC-466 | Cancer Biology: Cancer as a Genetic Disease | Cancer Biology | Nicole Walker | nsw4001@med.cornell.edu
2026-01-14 | 4:30PM - 6:00PM | ZRC-466 | Cancer Biology: Cell Cycle | Cancer Biology | Dr Jose Reyes | reyesj3@mskcc.org
2026-01-21 |  | No Class - NYC DOE Regents Administration | No Class - NYC DOE Regents Administration | N/A
2026-01-28 | 4:30PM - 6:00PM | ZRC-466 | Cancer Biology: Liquid Tumors | Cancer Biology | Dr Omar Abdel-Wahab | abdelwao@mskcc.org
2026-02-04 | 4:30PM - 6:00PM | Macklowe Building, 323 E. 61st St NY, NY 10065, Conference Room 530 | Cancer Biology Midterm Exam Preparation | Cancer Biology | Dr Debyani Chakravarty | chakravd@mskcc.org
2026-02-11 | 4:30PM - 6:00PM | Zoom | Cancer Biology Mid-Term Exam | Cancer Biology | Yaihara Fortis-Santiago/Raia Mohammed | fortissy@mskcc.org/mohammer@mskcc.org
2026-02-18 |  | No Class -Mid Winter Recess, schools closed | No Class -Mid Winter Recess, schools closed | N/A
2026-02-25 | 4:30PM - 6:00PM | ZRC-466 | Cancer Biology: Tumor Suppresors | Cancer Biology | Dr Pablo-Sanchez Vela | sanchezp@mskcc.org
2026-03-04 | 4:30PM - 6:00PM | ZRC-466 | Cancer Biology: Oncogenes and Cell Signaling | Cancer Biology | Dr Sarah Suenholz | phillis2@mskcc.org
2026-03-11 | 4:30PM - 6:00PM | Macklowe Building, 323 E. 61st St NY, NY 10065, Conference Room 530 | Cancer Biology: Targeted Therapies | Cancer Biology | Dr Debyani Chakravarty | chakravd@mskcc.org
2026-03-18 | 4:30PM - 6:00PM | ZRC-466 | Cancer Biology: Immunology | Cancer Biology | Dr Gabrielle Rizzutto | rizzutog@mskcc.org
2026-03-25 | 4:30PM - 6:00PM | ZRC-466 | Models of Cancer: Cells, Organoids and Animal Models | Cancer Biology | Jonathan Bermeo | bermeoj@mskcc.org
2026-03-26 | 4-7pm | TBD | STEM2City Career Fair
2026-04-01 | 4:30PM - 6:00PM | Macklowe Building, 323 E. 61st St NY, NY 10065, Conference Room 530 | Cancer Biology Final Exam Preparation | Cancer Biology | Dr Debyani Chakravarty | chakravd@mskcc.org
2026-04-08 |  | No Class -Spring Recess, schools closed | No Class -Spring Recess, schools closed | N/A
2026-04-15 | 4:30PM - 6:00PM | Zoom | Cancer Biology Final Exam | Cancer Biology | Yaihara Fortis-Santiago/Raia Mohammed
2026-04-22 | 1:00PM - 2:30PM | Macklowe Building, 323 E. 61st St NY, NY 10065, Conference Room 530 | Programming Languages - R/Python | Computational Sciences | Ino de brujin | debruiji@mskcc.org
2026-04-29 | 1: 00PM - 2:30PM | Macklowe Building, 323 E. 61st St NY, NY 10065, Conference Room 530 | Intro to Bioinformatics | Computational Sciences | Dr Francisco Sanchez-Vega | sanchezf@mskcc.org
2026-05-06 | 4:30PM - 6:00PM | Macklowe Building, 323 E. 61st St NY, NY 10065, Conference Room 530 | A Look Into Clinical Research-cBioPortal and OncoKB ¦ Data for Research & Health | Computational Sciences | Dr Nikolaus Schultz | schultzn@mskcc.org
2026-05-13 | 4:30PM - 6:00PM | ZRC-466 | Research and Development: How Biomarkers are found and used | Clinical/Translation Research | TBD | TBD
2026-05-20 | 4:30PM - 6:00PM | ZRC-466 | Clinical and Translational Research 101 | Clinical/Translation Research | Cristina Bravo | bravoc@mskcc.org
2026-05-27 |  | No Class -Eid al-Adha, schools closed | No Class -Eid al-Adha, schools closed | N/A
2026-06-03 | 4:30PM - 6:00PM | ZRC-466 | Clinical Research: Ethics | Clinical/Translation Research | Roy Cambria | cambriar@mskcc.org
2026-06-05 | 5-7pm | TBD | o Colloquium
2026-06-10 |  | No Class - NYC DOE Regents Administration | No Class - NYC DOE Regents Administration | N/A
2026-06-17 |  | No Class - NYC DOE Regents Administration | No Class - NYC DOE Regents Administration | N/A
2026-06-29 | 10:00AM - 4:00PM | Location TBD | SEP Summer Placement Orientation w/ SSP Students | Programmatic | Yaihara Fortis-Santiago/Raia Mohammed/Kevin Fisher
2026-06-29 | TBD | Location TBD | Lab Safety Training during Orientation | Programmatic | Environmental Health & Safety | pramans@mskcc.org; obrienp2@mskcc.org
6/29/2026 to 8/21/2026 |  |  | SEP Summer Research Placement | Programmatic | Yaihara Fortis-Santiago/Raia Mohammed/Kevin Fisher
2026-07-10 | 10-3pm | TBD | College Workshop
Date TBD July 2026 | TBD | American Museum of Natural History | NYC Science Research Mentoring Consortium College Workshop | NYC Science Research Mentoring Consortium | Maria Strangas & Arden Feil | mstrangas@amnh.org; afeil@amnh.org
Date TBD likely 2nd Thursday in August 2026 | 3:30PM - 6:00PM | American Museum of Natural History | Student Presentations: NYC Science Research Mentoring Consortium Summer Symposium | NYC Science Research Mentoring Consortium | Maria Strangas & Arden Feil | mstrangas@amnh.org; afeil@amnh.org
2026-07-13 | 4:30-6:30pm | TBD | Symposium
2026-08-21 | 10:30AM - 1:00PM | ZRC-Lobby | OSET HS Programs Poster Session | Programatic | Yaihara Fortis-Santiago/Raia Mohammed/Kevin Fisher
Last Updated on 12/4/25
Note on F30: Mohammed, Raia: Dr. Houcks-Loomis no longer at MSK.